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Dear Proposers,
The World Health Organization, hereinafter referred to as WHO, hereby invites prospective Proposers to submit a proposal in accordance with the General Conditions of Contract and the Terms of Reference as set out in this Request for Proposal (RFP).
To enable you to submit a proposal, please read the following attached documents carefully.
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If you are interested in submitting a proposal in response to this RFP:

1. Please acknowledge receipt of this RFP by completing and returning the Letter of Intent in Annex A, indicating your intention to submit a proposal or not, no later than 17:00 CET, 19 August 2026.

2. Please submit any requests for clarification no later than 17:00 CET 19 August 2026.

3. Please prepare your proposal in accordance with the requirements and procedures outlined in this RFP and submit it no later than 17:00 CET, 26 August 2026.

All WHO vendors are required to comply with the United Nations Supplier Code of Conduct. We encourage all Proposers to join the United Nations Global Compact and support the Women’s Empowerment Principles (WEP).

For guidance on how to register as a supplier in UNGM and use WHO’s e-tendering system, please refer to the following resources: Instructions on how to register with WHO and access WHO tenders , UNGM Help Center and UNGM/In-Tend support


We look forward to receiving your competitive proposals.
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[bookmark: _Toc236668395]Section 2: General Instructions to Proposers 
	[bookmark: _heading=h.vgp05xa8u3kz]GENERAL 

	1. [bookmark: _heading=h.x6r3b5tms1q1]About WHO
	[bookmark: _heading=h.f4l7ef55l7c5]The World Health Organization (WHO) was established in 1948 as a specialized agency of the United Nations. The objective of WHO (www.who.int) is the attainment by all peoples of the highest possible level of health. “Health”, as defined in the WHO Constitution, is a state of complete physical, mental and social well-being and not merely the absence of disease or infirmity. WHO's main function is to act as the directing and coordinating authority on international health work.

	2. [bookmark: _heading=h.kn35137rrimt]Scope 
	[bookmark: _heading=h.y5114trctop9]Proposers are invited to submit a proposal in line with the Terms of Reference (Section 5) and the requirements of this RFP, including any written amendments. A summary of the scope is provided in Section 3: Specific information about this RFP.

	3. [bookmark: _heading=h.14mtl0q1gz55]Interpretation of the RFP
	This RFP is conducted in accordance with Policies and Procedures of WHO, a summary of which is accessible at WHO’s website: WHO Procurement: principles and processes
Any proposal submitted will be regarded as an offer by the proposer and does not constitute or imply the acceptance of the proposal by WHO. WHO is under no obligation to award a Contract to any proposer as a result of this RFP.

	4. [bookmark: bookmark=id.cojg9ux1nkpc][bookmark: _heading=h.xt8qo6ntbbfk]Eligible Proposers
	Proposers shall have the legal capacity to enter into a binding contract with WHO. 
All WHO suppliers must abide to the UN Supplier Code of Conduct, which is available at the following link: UN Supplier Code of Conduct
Proposers must submit a signed Self-Declaration form included in this RFP.
Proposers will be excluded if:
· They are bankrupt, undergoing court administration, have suspended business, are under creditor arrangements, or in similar situations under national law.
· They or individuals with decision-making power have been found guilty of fraud, corruption, involvement in criminal organizations, money laundering, terrorism-related offenses, child labor, or human trafficking.
· They or such individuals have been found guilty of financial irregularities.
· They misrepresent or fail to provide required information under this RFP or during evaluation.
· They have a conflict of interest, as determined solely by WHO. This includes associations with firms involved in preparing specifications for this procurement or any other conflicting situation.
· They appear on sanction or ineligibility lists, including the UN Security Council, UN Ineligibility List, World Bank’s non-responsible vendors list, or World Bank ineligible firms and individuals list.
WHO may also exclude proposers for other reasons, at its discretion.


	[bookmark: _heading=h.fxle3qojmlbt]SOLICITATION DOCUMENTS

	5. [bookmark: _heading=h.w3mx6shr3cw4]Clarification of solicitation documents
	Proposers may request clarifications on any of the RFP documents no later than the date and time indicated in Section 3: Specific Information to this RFP. Any request for clarification must be sent in writing in the manner indicated in Section 3: Specific Information to this RFP. Explanations or interpretations provided by personnel other than the named contact person will not be considered binding or official.

WHO will provide the responses to clarifications through the method specified in Section 3: Specific Information to this RFP. No individual presentations or meetings with Proposers will be allowed before the proposal submission deadline. From the issuance of this RFP until final selection, contact with WHO officials is not permitted, except through formal queries as outlined, or if WHO initiates a presentation or meeting as per the RFP terms.

	6. [bookmark: bookmark=id.uxr5a3816f07][bookmark: _heading=h.fhaw71e4lg8w]Amendment of solicitation documents
	WHO may, at any time before the closing date for submission of proposals, for any reason, whether on its own initiative or in response to a clarification requested by a (prospective) proposer, modify the RFP by written amendment. Amendments will be made available to all prospective Proposers.

If the amendment is substantial or for other reasons, WHO may extend the Deadline for submission of proposals.

	[bookmark: _heading=h.9okde0d0789v]PREPARATION OF PROPOSALS

	7. [bookmark: _heading=h.ymuf1a2et404]Cost of preparation of the proposal
	The proposer shall bear all costs related to the preparation and/or submission of the proposal, regardless of whether its proposal is selected or not. WHO shall not be responsible or liable for those costs, regardless of the conduct or outcome of the procurement process.

	8. [bookmark: _heading=h.cdwhnkk95i9q]Language
	The proposal, as well as any and all related correspondence exchanged by the proposer and WHO, shall be written in the language(s) specified in Section 3: Specific Information to this RFP.

	9. [bookmark: _heading=h.hlzknps7k6cl]Documents comprising the’ proposal
	The proposal shall comprise of the forms requested in Section 7: Proposal forms as well as any associated documentation requested in the RFP

	10. [bookmark: _heading=h.6p7gye87m8r2]Technical proposal format and content
	The proposer must submit a technical proposal addressing all requirements in Section 4 (Evaluation Criteria), attaching the forms provided in Section 7 and responding to RFP requirement as described in Section 5 - Terms of Reference.
The technical proposal shall not include any price or financial information. A technical proposal containing material financial information may be declared non-responsive.

	11. [bookmark: _heading=h.k93dtpgolbzy]Financial proposal
	The financial proposal shall be prepared using the form provided in Section 7 and taking into consideration the requirements in the RFP. The proposal shall list all major cost components associated with the services, and the detailed breakdown of such costs.
Any output and activities described in the technical proposal but not priced in the financial proposal, shall be assumed to be included in the prices of other activities or items as well as in the final total price.
Prices and other financial information must not be disclosed in any other place except in the financial proposal.

	12. [bookmark: _heading=h.vah097jffkvj]Prices, Duties and taxes
	WHO is entitled to tax exemption by reason of the Privileges and Immunities it enjoys, subject to the conditions included in the WHO General Terms and Conditions in Section 6.

During bidding, vendors must submit prices excluding taxes. However, in jurisdictions / countries where VAT is mandatory, as evidenced by the vendor, the selected vendor will include VAT on invoices to WHO. The respective Finance team at Headquarters, Regional Office, or Country Office, will handle refund claims with the relevant authorities in accordance with applicable tax laws and procedures in that jurisdiction / country.

Any quantity or other discounts (e.g.: volume discounts) shall be clearly indicated. Prices quoted by the Proposer shall be fixed during the proposer’s performance of the contract.  Any adjustment or revision to the prices shall only be made effective upon agreement based on written amendment signed by both parties. 


	13. [bookmark: _heading=h.xke6e9o3n6l3]Currencies
	Prices may be quoted in US Dollar, or any currency of the proposer’s choice, unless otherwise stipulated in Section 3 Information Specific to the RFP.
However, for the purposes of comparison of all offers, WHO will convert the currency quoted in the offers to USD, in accordance with the UN Operational Rate of Exchange on the closing date for proposal submission specified in Section 3: Specific information about this RFP.

	14. [bookmark: _heading=h.6tz2r72ogmci]Proposal validity period 
	Proposals shall remain valid for the period specified in Section 3: Specific information about this RFP commencing on the deadline for submission of proposals. A proposal valid for a shorter period may be rejected by WHO and rendered non-responsive. 
During the proposal validity period, the proposer shall maintain its original proposal without any change, including the availability of the key personnel, the proposed rates and the total price. In exceptional circumstances, prior to the expiration of the proposal validity period, WHO may request Proposers to extend the period of validity of their proposals. 

	15. [bookmark: bookmark=id.82450ir2qu87][bookmark: _heading=h.e7kzcqi6i8iq]Joint Venture, Consortium or Association
	Two or more entities may form a joint venture or consortium and submit a joint proposal offering to jointly provide the services described in the proposal. Such a proposal must be submitted in the name of one member of the consortium hereinafter the “lead organization". The lead organization will be responsible for undertaking all negotiations and discussions with, and be the main point of contact for, WHO. The lead organization and each member of the consortium will be jointly and severally responsible for the proper performance of the contract

	16. [bookmark: bookmark=id.lmqpnrvtv3un][bookmark: _heading=h.1g8clriclrep]Only one proposal
	Each proposer, including individual members of any Joint Venture, may submit only one proposal—either independently or as part of a Joint Venture.
Proposals will be rejected if any of the following apply:
· They share at least one controlling partner, director, or shareholder.
· One has received a direct or indirect subsidy from another.
· They have the same legal representative for this RFP.
· They are related in a way that gives access to or influence over another’s proposal.
· They are subcontractors to each other, or a subcontractor also submits a separate proposal as a lead proposer.
· Key personnel are proposed in more than one team (this does not apply to subcontractors appearing in multiple proposals).

	17. [bookmark: _heading=h.tgqypuf01szn]Alternative proposals
	Unless otherwise specified in Section 3: Specific information about this RFP, alternative proposals shall not be considered. If submission of alternative proposal is allowed in Section 3: Specific information about this RFP, a proposer may submit an alternative proposal but only if it also submits a proposal conforming to the RFP requirements. Where the conditions for its acceptance are met, or justifications are clearly established, WHO reserves the right to award a contract based on an alternative proposal.

	18. [bookmark: _heading=h.ernwcr8gf3vx]Pre-proposal conference
	When appropriate, a pre-proposal conference will be held at the date, time, and location specified in Section 3: Specific information about this RFP. If marked as mandatory, non-attendance will result in ineligibility to submit a proposal. If not mandatory, non-attendance will not lead to disqualification.

	19. [bookmark: _heading=h.p4uo34gsv622]Site inspection
	If specified in Section 3: Specific information about this RFP, a site inspection will be held at the indicated date, time, and location, following the given instructions. If marked as mandatory, failure to attend will render a proposer ineligible. If not mandatory, non-attendance will not lead to disqualification. Proposers are responsible for their own visa arrangements. The site inspection is for background information only, and any information provided is not binding unless confirmed by WHO in writing.

	[bookmark: bookmark=id.6ltrdqkpnilq][bookmark: _heading=h.nzqa22t39zw9]SUBMISSION AND OPENING OF PROPOSALS

	20. [bookmark: _heading=h.a2yx8fcdbfi8]Instruction for proposal submission
	The proposer shall submit a complete proposal in the format and with the documents required in Section 3: Specific information about this RFP, using the delivery method specified therein. Submission of a proposal implies that the proposer has accessed, read, understood, and agrees to comply with WHO’s General and Contractual Conditions in Section 6.

	21. [bookmark: _heading=h.oq4x8tat4mh5]Deadline for proposal submission
	Complete proposals must be received by WHO in the manner, and no later than the date and time, specified in Section 3: Specific information about this RFP. In case of any doubt regarding the time zone, Proposers should refer to Section 3: Specific information about this RFP. It is the sole responsibility of Proposers to ensure their proposal is received by the stated deadline.

Late submissions will not be possible or accepted. Proposers are strongly advised to take all necessary steps to ensure timely submission. WHO accepts no responsibility for proposals that are delayed due to technical issues and will consider only the actual date and time of receipt.

WHO may, at its discretion, extend the proposal submission deadline by amending the solicitation documents in accordance with Clause 6 (Amendment of solicitation documents) of Section 2. In such cases, the new deadline will apply to all Proposers.


	22. [bookmark: _heading=h.nuhjmy6putz5]Withdrawal, substitution and modification of proposals
	The proposer may withdraw its proposal any time after the proposal’s submission and before the tender closing date of the proposals, provided a written and signed notice of the withdrawal is received by WHO prior to the closing date for the submission of proposals. No Proposal may be withdrawn in the interval between the closing date for submission of proposals and the expiration of the proposal validity period.

	23. [bookmark: _heading=h.tpmpmkjic2lq]Proposal opening



	Proposals will be opened after the deadline for proposal submission by the proposal opening committee
There will be separate proposal openings for technical and financial proposals. 
The opening panel will open only the financial proposals of suppliers who meet the minimum criteria of the technical evaluation. 

	EVALUATION OF PROPOSALS

	24. [bookmark: _heading=h.6fwwntqov74g]Evaluation of proposals
	WHO shall evaluate a proposal using only the methodologies and criteria defined in this RFP. No other criteria or methodology shall be permitted.

WHO shall conduct the evaluation solely on the basis of the submitted technical and financial proposals.
Evaluation of proposals shall be undertaken in the following steps:
(i) preliminary examination.
(ii) evaluation of minimum eligibility and qualification (if pre-selection is not done) / mandatory requirements
(iii) evaluation of technical proposals on weighted scoring; and
(iv) evaluation of financial proposals.

	25. [bookmark: bookmark=id.s60iuwcw0vba][bookmark: bookmark=id.jlxnnalhpwu3][bookmark: _heading=h.fbinsqjyjl88]Preliminary examination
	WHO shall examine the proposals to determine whether they are complete with respect to minimum documentary requirements, whether the documents have been properly signed, and whether the proposals are generally in order, among other indicators that may be used at this stage. WHO reserves the right to reject any proposal at this stage. Technical proposals found to contain financial proposal or pricing information will be rejected.

	26. [bookmark: _heading=h.7ndfl9vn0io2]Evaluation of eligibility and qualification
	Eligibility and qualification of the proposer will be evaluated against the minimum eligibility and qualification requirements specified in Section 4: Evaluation Criteria and in Clause 4 (Eligible Proposers) in Section 2.

	27. [bookmark: _heading=h.qjtnnd87hazs]Evaluation of technical and financial proposals
	After the preliminary evaluation, the panel will assess technical proposals based on their responsiveness to the Terms of Reference and other RFP documents, using the evaluation criteria, sub-criteria, and point system in Section 4: Evaluation Criteria. Proposals that do not meet the minimum technical score will be considered non-responsive.

Only the financial proposals of technically qualified Proposers will be opened and evaluated in the second stage.

If required, WHO may invite technically responsive Proposers for a presentation, with conditions provided in the RFP. Presentations may be held at WHO offices or via tele/videoconference.

The applicable evaluation method is indicated in Section 3: Specific information about this RFP, typically the combined scoring method based on both technical and financial scores.

	28. [bookmark: bookmark=id.keqnobbq1o5c][bookmark: _heading=h.ns2z6aq0p7zm]Clarification of proposals
	WHO may request clarifications or additional information in writing from Proposers at any stage of the evaluation. Responses must not alter the substance or price of the proposal, except to confirm corrections of any arithmetical errors identified by WHO, as outlined in the General Instructions to Proposers.

	29. [bookmark: _heading=h.c37vdj9i8deb]Nonconformities, reparable errors and omissions
	Provided that a proposal is substantially responsive, WHO may request the proposer to submit the necessary information or documentation within a reasonable period in order to rectify nonmaterial nonconformities or omissions in the proposal related to documentation requirements. Such omission shall not be related to any aspect of the price of the proposal. Failure of the proposer to comply with the request may result in the rejection of its proposal.
For financial proposals that have been opened, WHO shall check, and correct arithmetical errors as follows:
a) if there is a discrepancy between the unit price and the line item total that is obtained by multiplying the unit price by the quantity, the unit price shall prevail and the line item total shall be corrected, unless in the opinion of WHO there is an obvious misplacement of the decimal point in the unit price; in which case, the line item total as quoted shall govern and the unit price shall be corrected;
b) if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail, and the total shall be corrected; and
c) if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetical error, in which case the amount in figures shall prevail.
If the proposer does not accept the correction of errors, its proposal shall be rejected, and its proposal security may be forfeited.

	[bookmark: _heading=h.e07mmoniuipr]AWARD OF CONTRACT

	30. [bookmark: _heading=h.cqlm0tx7vgr1]Award criteria, award of Contract
	Before the expiration of proposal validity, WHO will award the Contract to the qualified proposer based on the criteria set out in the tender document.
WHO reserves the right to:
a) award the Contract to any proposer, even if not the lowest.
b) award separate contracts for different parts, components, or items to one or more proposers, even if not the lowest.
c) accept or reject any proposal or cancel the entire solicitation process at any time before award, without liability or obligation to inform proposers of the reasons.
d) award the Contract based on WHO’s specific objectives to the proposer whose offer best meets the Organization’s needs.
e) decide not to award any contract.

	31. [bookmark: _heading=h.rsmen3291b6c]Right to vary requirements at time of award
	At the time the Contract is awarded, WHO reserves the right to revise the scope of the work or to increase or decrease the quantity of services originally specified in Section 5: Terms of Reference / Schedule of requirements, and without any change in the unit prices or other terms and conditions of the proposal and the solicitation document. 

	32. [bookmark: _heading=h.dmaln69xfb1]Notification of award
	Prior to the expiration of the period of proposal validity, WHO will notify the successful proposer in writing via email or via a notification from e-tendering system. After signing the contract with successful vendor, the unsuccessful vendors will be sent a regret notification.

	33. [bookmark: _heading=h.aohb8n4ja92m] Payment terms
	Full payment of 100% is due within 30 days following receipt and acceptance of services, upon receipt of the invoice.

	34. [bookmark: bookmark=id.29kq2mokyedi][bookmark: _heading=h.785azteuxeyx]Debriefing
	WHO does not routinely offer debriefings to unsuccessful proposers. However, for tenders over $300,000 or complex tenders, WHO may provide a debriefing upon written request. The request must be submitted within 30 calendar days of receiving the notification of non-award.
The debriefing aims to highlight the strengths and weaknesses of the proposer’s submission to help improve future proposals. It will not include discussion of other proposals or comparisons. Debriefings will be conducted only through in-person meetings, teleconference, or videoconference.

	35. [bookmark: _heading=h.qdj6xnwy71hg]Proposal complaint
	When a supplier believes that WHO did not follow its own procurement rules, the supplier may choose to raise a formal complaint. The Procurement Complaint Mechanism is only available to suppliers who:
· Participated in a competitive procurement process and were not awarded a contract; and 
· The value of the contract award is higher than US$ 300,000.
A formal complaint must be submitted in writing within one month of the notification of the outcome of the competitive bidding process, to the following email address: procurementcomplaint@who.int and must include the minimum information detailed on the WHO website (WHO Procurement: frequently asked questions).


	36. [bookmark: _heading=h.wy4q79uftunn]Publication of Contract award
	WHO publishes on its contract awards webpage the list of contracts for acquired goods and services of a value of USD 25 000 or more. This information is published with due observance of the requirements of confidentiality and security. Further procurement data about WHO can be obtained through WHO’s Procurement Report or at UNGM’s Annual Statistical Report on UN Procurement.. 

	37. [bookmark: _heading=h.wagt6vdmbid1]Performance Security
	This is not mandatory; however, if specified in Section 3: Specific information about this RFP, the successful Proposer must provide a performance security in the stated amount and form within the specified timeframe after receiving the contract from WHO.


[bookmark: _heading=h.lmtk7jtx10lq]

[bookmark: _Toc236668396]Section 3: Specific Information to this RFP
The following specific information shall complement, supplement or amend the provisions in Section 2: General Instructions to Proposers. In case there is a conflict, the provisions herein shall prevail over those in Section 2: General Instructions to Proposers.
	Instructions to Proposer’s article
	Specific Instructions / Requirements

	Scope of RFP 
(Article 2)

	The reference number of this Request for Proposal (RFP) is HO-SHQ-RFP-26-2023
The services include Supporting WHO in Accelerating Introduction of RSV Vaccine into the Low and Middle-Income Countries (LMICs) as further described in Section 5 of this RFP.
The purpose of this RFP is to establish an Agreement for Performance of Work (APW) Contract.


	[bookmark: bookmark=id.h6dbmhlx9g7w]Clarification of the RFP
(Article 5)
	a) Contact details for clarification of solicitation documents should be sent to WHO by: 
 ×    Email address: gsellp@who.int
 ☐    Via UNGM e-tendering portal: Questions are to be submitted via the UNGM “Correspondence” tab

b) Deadline for submitting requests for clarifications / questions:
Date: 19 August 2026
Time 17:00 CET
City and Country: Geneva, Switzerland
Responses to requests for clarification will be communicated in writing by WHO to all proposers via same medium as stated above. 

	Language of the RFP (Article 8) 
	Language of this proposal shall be in English

	Currency of proposal (preferred) 
(Article 13)
	Prices included in the proposal shall be preferably quoted in USD

	[bookmark: bookmark=id.oh1mec6vslej][bookmark: bookmark=id.nbwxjq6njkbm]Proposal validity (Article14)
	Six months from the deadline for proposal submission.

	[bookmark: bookmark=id.67qlm6r7v6ft][bookmark: bookmark=id.mwbta5w210oo]Alternative proposals (Article 17)
	N/A

	[bookmark: bookmark=id.nw8yrrxfdlj9]Pre-proposal conference 
(Article 18).
	N/A 

	[bookmark: bookmark=id.qqh8bzt1mgwq]Site Inspection 
(Article 19)
	N/A





	Instructions for submission of Proposals 
(Article 20)

	Allowable manner of submitting proposals:
☐ E-tendering (In-Tend): 
×      Email:  gsellp@who.int

ATTENTION: Proposals which do not comply with the selected method of submission may be rejected.

	Deadline for proposal submission 
(Article 21)
	Public proposal opening will not be held
CLOSING DATE: 26 August 2026
CLOSING TIME: 17:00 CET

	[bookmark: bookmark=id.aiauuj74lmga]Evaluation of technical and financial proposals (Article 24)
	Evaluation will be based on the combined scoring method using a distribution 70:30 of Technical Proposal to Financial Proposal respectively. This means that Technical Proposal will take [TP Marks 70%]. and Financial Proposal will take [FP Mark 30%]
To be technically compliant, Proposers must obtain a minimum threshold of [Min Tech Score 70% of maximum points.

	[bookmark: bookmark=id.mqptil8siny6]Performance Security (Article 37)
	 Not Required


[bookmark: bookmark=id.cogp46mrhz2w]
[bookmark: _heading=h.j60i1i8qp6hf]


[bookmark: _Toc236668397]Section 4: Evaluation Criteria

The evaluation criteria are divided into two.

A- Technical Evaluation Criteria Weighing 70%
B- Financial Evaluation Criteria Weighting 30%

A- TECHNICAL EVALUATION CRITERIA

The technical evaluation criteria will follow the below process

1.	Preliminary examination.
2.	Evaluation of minimum eligibility and qualification/mandatory requirements.
3.	Technical Proposal Weighted Scoring.

1. Preliminary examination 

WHO shall examine the proposals to determine whether they are complete with respect to minimum documentary requirements, whether the documents have been properly signed, and whether the proposals are generally in order, among other indicators that may be used at this stage. WHO reserves the right to reject any proposal at this stage. Technical proposals found to contain financial proposal or pricing information will be rejected

2. Minimum eligibility and qualifications (Mandatory Requirements) 
The vendors proposals will be assessed on pass and fail methodology and failure in any of the criteria may exclude the vendor for consideration at next stage of weighted scoring. WHO deserves the right to seek clarification when a proposal contains unclear or ambiguous information that makes it difficult to evaluate the submission fairly against the published technical criteria.

	Item
	Minimum eligibility and qualifications (Mandatory Requirement)
	Required supporting documents 
	Pass /Fail?

	1. 
	Corporate status of the company: Proposer is a legally registered entity
	Vendor to provide proof of registration or accreditation in form of incorporation certificate, trading licences by filling the form in Annex D
	

	2. 
	Vendor Eligibility: Vendor is not suspended, nor otherwise identified as ineligible, by any UN Organization, the World Bank Group or any other International Organization in accordance with Section 2: Clause 4.
	Vendor to declare that its company is eligible by filling the form in Annex D
	

	3. 
	Conflict of Interest:  The Proposer must have no conflict or perceived conflict of interest
	Vendor to declare that he has no conflict / perceived conflict of interest by filling the form in Annex E
	

	4. 
	Bankruptcy: Proposer has not declared bankruptcy, is not involved in bankruptcy or receivership proceedings, and there is no judgement or pending legal action against the vendor that could impair its operations in the foreseeable future
	Vendor to declare that he has no conflict / perceived conflict of interest by filling the form in Annex E
	

	5. 
	Non-performing contracts and History of Litigation: Vendor must declare that during the last 3 years, that its company has no non-performing contracts because of its company’s default and that its company has no consistent history of court/arbitral award decisions against itself.
	Vendor to declare that its company is eligible by filling the form in Annex D
	

	6. 
	Company / Experience- The proposer must have minimum 7 years of relevant experience (For Joint Venture/Consortium/Association, all Parties cumulatively should meet the requirement).
	Company should provide a list of relevant projects that should demonstrate at least 7 year of relevant experience. Please fill form D.
	

	7. 
	Past performance: The proposer must submit at least: a) List of any  relevant/comparable contracts and b)  Any   reference letters for related services.
	Company / respondent should provide  one  reference letters related to the current project, Fill form D for the list of relevant projects
	



N.B Failure in any of the above mandatory criteria will result in the vendors proposal not being considered for weighted Scoring. 

3. Weighted Scoring Criteria 

Vendors who pass the preliminary and minimum eligibility requirements will have their proposals evaluated using a weighted scoring system, depending on the quality and clarity of the submitted proposal. Each proposal will be assessed against the set criteria, and a weighted score will be calculated to determine the most technically and/or financially advantageous offer.


The number of points which can be obtained for each evaluation criterion is specified below and indicates the relative significance or weight of the item in the overall evaluation process. As indicated, these points or even the criteria can be changed depending on the RFP requirements 

The scoring scale per criteria was defined as follows:

	Criteria evaluated as:
	Based on the following supporting evidence:
	Corresponds to the % of maximum score

	Excellent and fully detailed 
	Excellent evidence of ability to exceed requirements
	100%

	Substantially detailed 
	Good evidence of ability to exceed requirements
	80%

	Averagely detailed
	Satisfactory evidence of ability to support requirements
	50%

	Marginally detailed
	Marginally acceptable or weak evidence of ability to support requirements
	20%

	Very minimally detailed 
	Lack of evidence to demonstrate ability to comply with requirements
	10%

	No submission
	Information has not been submitted or is unacceptable
	0%



 Weighted Criteria and maximum Score for each criteria is as follows. 

	Section 1. Organizational Capacity and Industry Standing
	Max Points 

	1.1
	Proven Organizational Capability. The submitted proposal demonstrates a clear and robust organizational structure, effective project management systems, and the capacity to self-finance the assignment.
	100

	1.2
	Relevant Technical Experience in Similar Contexts: The submitted proposal provides evidence of verifiable evidence of completed projects of comparable scope and complexity, preferably in the same country or region or UN or any comparable International Organizations, delivered in the last 7 years. Proposals must demonstrate relevance to the subject matter and include project titles, duration, scope, and outcomes.
	200

	Total Section 1
	300

	Section 2. Proposed methodology approach and implementation plan

	

	2.1
	Clear and Detailed Understanding of the Terms of Reference - The submitted proposal demonstrates a clear grasp of the objectives and scope of the assignment, addresses all key components of the Terms of Reference, and reflects appropriate emphasis on each task area. Responses must refer to specific sections of the TOR and align with stated deliverables.
	120

	2.2
	Proposed Approach and Methodology: The submitted proposal presents a structured, realistic methodology that goes beyond repeating the TOR and includes details on resource use, stakeholder engagement (where applicable), innovative practices (if any), and value-added elements. The methodology must show logical progression from planning to execution.
	200

	2.3
	Implementation and Operational Management Plan: The submitted proposal provides a comprehensive plan detailing how the assignment will be implemented and managed including a sequenced and time-bound work plan with key activities, timelines, and deliverables (Gantt Chart etc) and an explanation of how tasks will be organized, controlled, and monitored
	80

	Total Section 2
	400

	Section 3. Management Structure and Key Personnel
	Max Points

	3.1
	Management structure: The proposal presents a clear and functional team structure that supports effective implementation and contract management. The management roles, reporting lines, and responsibilities are clearly defined and appropriate for the scope of the assignment.
	100

	3.2
	Key Personnel Qualifications: The proposal includes qualified individuals for each key role (Team Leader, Senior Expert, Junior Expert), with CVs demonstrating their experience and competencies in line with the assignment requirements.
	200

	Total Section 3
	300

	Grand Total 
	1,000



NOTE
a) A minimum of 70% is required to pass the technical evaluation. Non-technically compliant proposals will not be opened for commercial evaluation

b) Rating the Technical Proposal (TP):
TP Rating = (Total Score Obtained by the Offer / Max. Obtainable Score for TP) x 100

B- FINANCIAL EVALUATION

Once the technical evaluation is finalized, all evaluation panel members will sign the technical evaluation report. Only financial proposals from proposers who meet the minimum technical score, as indicated above, will be opened and evaluated. Proposals that do not meet the minimum technical threshold will be rejected.

The formula for the rating of the proposals will be as follows:

Rating the Technical Proposal (TP):
TP Rating = (Total Score Obtained by the Offer / Max. Obtainable Score for TP) x 100

Rating the Financial Proposal (FP):
FP Rating = (Lowest Priced or Cost Offer / Price or Cost of the Offer Being Evaluated) x 100

Total Combined Score:
[bookmark: _heading=h.qfud15nire24][bookmark: bookmark=id.u0dqrdy6mei3][bookmark: bookmark=id.ojmgwbktavrm](TP Rating) x (Weight of TP [70%]+ (FP Rating) x (Weight of FP i.e.[30%  = Total Combined and Final Rating of the Proposal.

[bookmark: _Toc236668398]Section 5: Terms of Reference -Services 

5.1 [bookmark: _heading=h.1cr6b099odi3]Introduction

WHO is seeking for a qualified, eligible and competent proposer for Supporting WHO in Accelerating Introduction of RSV Vaccine into the Low and Middle-Income Countries (LMICs). 
Respiratory syncytial virus (RSV) is a leading cause of acute lower respiratory infections and associated hospitalizations in infants and children throughout the world, estimated to cause over 100,000 deaths each year. Over 95% of infections and 97% of deaths occur in children living in low- and middle-income countries (LMICs). After decades of research, vaccines for use during pregnancy and infant monoclonal antibodies have been licensed to protect infants from severe RSV disease. In response to new global recommendations issued by WHO SAGE in 2024 for maternal vaccine and monoclonal antibody use and following the WHO prequalification of the maternal vaccine in early 2025, countries are preparing for RSV introduction. While introduction of RSV immunization has begun in high-income countries, immunization has not started in LMICs. 
WHO is looking for proposer to support in accelerating the introduction of RSV vaccines in LMICs by providing technical, operational, and strategic support to global and country-level initiatives.

5.2 Characteristics of the Contractor is 

5.2.1 [bookmark: _heading=h.blpjpeuve8nq]Status
[bookmark: _heading=h.ta4xh6trkb6h]The Proposer shall be a Company/entity operating in the field of RSV or related vaccine field.

[bookmark: _heading=h.l958qsxaai5n][bookmark: _heading=h.1tzhl0eqeqkc]
5.2.2 [bookmark: _heading=h.e1baeal1pxqh]Previous experience
[bookmark: _heading=h.38v5c2ejfge1]Mandatory:

· Expertise in RSV or other vaccine-preventable respiratory diseases, including epidemiology and immunization approaches. 
· Knowledge of immunization policy development and vaccine introduction processes, with experience in RSV or other vaccine-preventable diseases preferred. 
· Proven experience in vaccine advocacy, project management, and coordination of high-level events, preferably in a global health context; experience related to RSV or other immunization programmes is an asset. 
· Demonstrated experience working with WHO, international organizations, or major public health institutions in immunization, vaccine introduction, or public health; RSV-specific experience is desirable but not essential. Experience successfully planning, coordinating, and delivering high-level events, stakeholder engagements, or advocacy campaigns. Experience coordinating with multiple stakeholders and partners in complex, multi-country settings 
· Experience developing technical reports, policy briefs, and guidance documents for diverse stakeholders. Experience in LMIC country support, including field experience or regional roles

5.2.3 [bookmark: _heading=h.nukluvy91ogi]Staffing
[bookmark: _heading=h.5kxao5x35ssh]The selected contractor is expected to dedicate the following human resources to the project:

· A project manager of an adequate level of qualification and experience (please attach resume to your proposal) shall be dedicated to the project.
· The designated project manager that should be the same all along implementation, including consideration in contingency plans in case the focal point is absent.
· A senior advisor(s) with extensive knowledge of RSV
· Sufficient capacity and knowledge is required to cover the following areas of expertise:
· Solid technical knowledge of RSV, including epidemiology, prevention strategies, and immunization approaches
· Understanding of vaccine policy development and decision-making processes (e.g., NITAGs)
· Familiarity with global immunization partners and mechanisms, including World Health Organization, Gavi, the Vaccine Alliance, and UNICEF 
· Knowledge of advocacy, demand generation, and risk communication in public health
· WHO pays utmost attention to the level of qualification and experience of the individuals involved, and to continuity in the services. The profiles (no individual names required) of the personnel proposed for these services should be included in the technical proposal.
· All staff with full professional working proficiency/native or bilingual proficiency in English. 

The Proposer is expected to outline the roles and responsibilities of those staff in the technical proposal. 
Activities will be carried in normal working hours of Geneva time zone. 

5.2.4 [bookmark: _heading=h.g8y6dz79u934]Work to be performed 
[bookmark: _h37nlx6e7x84]1. Support WHO's role in providing global technical guidance and implementation strategies for maternal RSV vaccine introduction 
· Output 1.1: Support WHO/IVB to coordinate the development and finalization of WHO operational guidance for maternal RSV vaccine introduction, including implementation pathways integrating immunization and antenatal care (ANC) services.
· Output 1.2: Coordinate the development of supplementary implementation tools for WHO operational guidance for maternal RSV vaccine introduction, including health worker training packages, job aids, and PIE materials.
· Output 1.3: Develop protocols for undertaking RSV vaccine effectiveness studies in low- and middle-income countries (LMICs), through adaptation of existing protocols to LMIC implementation settings. Support preparation of finalized protocols for dissemination through IVB’s RSV platform for use by early introducing LMICs.
· Output 1.4: Develop and update technical briefing materials, presentations, and evidence summaries on RSV disease burden, immunization strategies, and policy considerations for internal and external stakeholders.
[bookmark: _gp3a0fue5gf7]2. Drive evidence generation and implementation research to inform RSV policy and scale-up
· Output 2.1: Provide scientific support to the RSV Impact Study in Africa through active participation on the Scientific Advisory Committee, and provide quarterly progress updates to IVB on study status, implementation progress, and key developments.
· Output 2.2: Actively participate in the design, implementation, monitoring, and analysis of the RSV vaccine demonstration project in Pakistan, including coordination with implementing partners and ensuring regular updates to IVB on project progress.
· Output 2.3: Provide technical support and collaborate with IVAC on the development, refinement, interpretation, and application of RSV disease burden estimates and country introduction models.
· Output 2.4: Synthesize evidence on RSV vaccine effectiveness, safety, implementation experiences, and operational challenges from LMIC settings through study analyses, technical reports, and dissemination products.
· Output 2.5: Provide technical input to partners and early adopter countries during planning and rollout, including documentation of readiness assessments, implementation recommendations, and follow-up actions.  
· Output 2.6: Conduct technical review of WHO RSV-related scientific and programmatic outputs for scientific accuracy.
· Output 2.7: Document and synthesize lessons learned from early adopter countries and demonstration projects.
· [bookmark: _rzio6y2z1o6d]Output 2.8: Support and/or review post-introduction assessments and evaluation activities where applicable (revising tools for global use).
· Output 2.9: Review work that WHO has commissioned to estimated country-level RSV BoD in LMICs that adds to database on global burden of RSV disease.
3. Strengthen global partnerships and stakeholder coordination for RSV immunization
· Output 3.1: Support WHO’s multi-stakeholder initiatives promoting RSV immunization, including the RSV coordination team (co-lead with Gavi) and strategic working groups.
· Output 3.2: Facilitate WHO’s engagement with the MIRNA consortium (8 countries) and RSV early adopter network (5 countries), including technical exchanges, progress tracking, and dissemination of lessons learned.
· Output 3.3: Support IVB in convenings of regular and ad hoc technical consultations with WHO partners and stakeholders (e.g., RITAG, NITAG, Gates Foundation, Gavi, etc.) on RSV immunization products and country introductions, and document key outcomes and follow-up actions.
· [bookmark: _gr903n9utzgt]Output 3.4: Support and maintain stakeholder mapping and engagement, including meeting summaries and action tracking tools.
4. Support IVB in and global advocacy initiatives to accelerate RSV introduction
· Output 4.1: Plan and coordinate global RSV events and high-level stakeholder engagements, including WHA side events and international convenings.
· Output 4.2: Support establishment and operationalization of a global RSV collaboration platform and community of practice including stakeholder engagement mechanisms.
· Output 4.3: Maintain and regularly update a country tracking tool to monitor progress across Gavi-supported countries and capture partner updates related to RSV introduction and implementation efforts. The tracker will serve as a key coordination and monitoring tool, providing a structured basis for discussion during Coordination Team meetings and facilitating information sharing among partners.
· Output 4.4: Organize meetings and forums to advance evidence sharing and alignment on RSV vaccine introduction.
· Output 4.5: Support development and dissemination of communication and advocacy materials for key stakeholders, including through the WHO website.
· [bookmark: _nkbhl2c92lg7]Output 4.6: Support development of briefing materials and evidence summaries for policy discussions and decision-makers.
[bookmark: _heading=h.yfb1h1wgdhvo]
5.3 Key requirements

· [bookmark: _heading=h.d69lxdgsmlj2]Advanced WHO global guidance for maternal RSV vaccine introduction by coordinating the development of operational guidance, implementation tools, technical protocols, and evidence-based briefing materials to support country readiness and integration of RSV vaccination into maternal immunization programmes. 
· Strengthened the evidence base for RSV policy and implementation by supporting vaccine effectiveness studies, demonstration projects, disease burden modelling, implementation research, quality assurance, and the synthesis of evidence and lessons learned from early adopter countries. 
· Enhanced global coordination and partnerships by facilitating collaboration among WHO, countries, research institutions, donors, and technical partners; coordinating technical consultations and working groups; and strengthening stakeholder engagement, knowledge exchange, and progress monitoring. 
· Supported global advocacy and country introduction efforts by planning high-level events and stakeholder engagements, establishing coordination platforms and monitoring tools, organizing evidence-sharing forums, and developing communication, advocacy, and policy briefing materials to accelerate equitable RSV vaccine introduction.


5.4 [bookmark: _heading=h.k6actlec53hf]Place of Performance

Remotely.

5.5 [bookmark: _heading=h.i8e146hta6sg]Timelines
[bookmark: _heading=h.2vsr13ttglej]
Approximately 18-24 months, starting in September 2026.

The timelines presented below are indicative and may be adjusted during contract period in response to external factors, including evolving WHO priorities, partner activities, country readiness, and the availability of emerging evidence. While some outputs have clear milestones, others represent ongoing technical support or activities that are implemented multiple phase. In these cases, the timeline reflects key milestones (e.g., establishment or initial delivery), with continued operational support/refinement/maintenance throughout the contract period as needed. 

	Output
	Milestone

	Deliverable 1: Support WHO's role in providing global technical guidance and implementation strategies for maternal RSV vaccine introduction 

	Output 1.1: Support WHO/IVB to coordinate the development and finalization of WHO operational guidance for maternal RSV vaccine introduction, including implementation pathways integrating immunization and antenatal care (ANC) services. 
	Q4 - 2026

	Output 1.2: Coordinate the development of supplementary implementation tools for WHO operational guidance for maternal RSV vaccine introduction, including health worker training packages, job aids, and PIE materials.
	Q2 - 2027

	Output 1.3: Develop protocols for undertaking RSV vaccine effectiveness studies in low- and middle-income countries (LMICs), through adaptation of existing protocols to LMIC implementation settings. Support preparation of finalized protocols for dissemination through IVB’s RSV platform for use by early introducing LMICs. 
	Q4 - 2027

	Output 1.4: Develop and update technical briefing materials, presentations, and evidence summaries on RSV disease burden, immunization strategies, and policy considerations for internal and external stakeholders. 
	Quarterly (Q3 2026–Q3 2028)

	Deliverable 2: Drive evidence generation and implementation research to inform RSV policy and scale-up 

	Output 2.1: Provide scientific support to the RSV Impact Study in Africa through active participation on the Scientific Advisory Committee, and provide quarterly progress updates to IVB on study status, implementation progress, and key developments. 
	Quarterly (Q3 2026–Q3 2028)

	Output 2.2: Actively participate in the design, implementation, monitoring, and analysis of the RSV vaccine demonstration project in Pakistan, including coordination with implementing partners and ensuring regular updates to IVB on project progress. 
	Quarterly (Q3 2026–Q3 2028)

	Output 2.3: Provide technical support and collaborate with IVAC on the development, refinement, interpretation, and application of RSV disease burden estimates and country introduction models through their viewhub platform. 
	Quarterly (Q3 2026–Q3 2028)

	Output 2.4: Synthesize evidence on RSV vaccine effectiveness, safety, implementation experiences, and operational challenges from LMIC settings through study analyses, technical reports, and dissemination products. 
	Q2 - 2028

	Output 2.5: Provide technical input to partners and early adopter countries during planning and rollout, including documentation of readiness assessments, implementation recommendations, and follow-up actions. 
	Quarterly (Q3 2026–Q3 2028)

	Output 2.6: Conduct technical review of WHO RSV-related scientific and programmatic outputs for scientific accuracy. 
	Quarterly (Q3 2026–Q3 2028)


	Output 2.7: Document and synthesize lessons learned from early adopter countries and demonstration projects. 
	Q3 - 2028

	Output 2.8: Support and/or review post-introduction assessments and evaluation activities where applicable (revising tools for global use). 
	Q3 - 2028

	Output 2.9: Review work that WHO has commissioned to estimated country-level RSV BoD in LMICs that adds to database on global burden of RSV disease. 
	Q1 - 2027

	Deliverable 3: Strengthen global partnerships and stakeholder coordination for RSV immunization 

	Output 3.1: Support WHO’s multi-stakeholder initiatives promoting RSV immunization, including the RSV coordination team (co-lead with Gavi) and strategic working groups. 
	Quarterly (Q3 2026–Q3 2028)

	Output 3.2: Facilitate WHO’s engagement with the MIRNA consortium (8 countries) and RSV early adopter network (5 countries), including technical exchanges, progress tracking, and dissemination of lessons learned. 
	Q4 – 2026
Q4 - 2027

	Output 3.3: Support IVB in convenings of regular and ad hoc technical consultations with WHO partners and stakeholders (e.g., RITAG, NITAG, Gates Foundation, Gavi, Sabin etc.) on RSV immunization products and country introductions, and document key outcomes and follow-up actions. 
	Quarterly (Q3 2026–Q3 2028)

	Output 3.4: Support and maintain stakeholder mapping and engagement, including meeting summaries and action tracking tools. 
	Q1 – 2027 (initial stakeholder mapping)
Quarterly (Q2 2027–Q3 2028)


	Deliverable 4: Support IVB in and global advocacy initiatives to accelerate RSV introduction 

	Output 4.1: Plan and coordinate global RSV events and high-level stakeholder engagements, including WHA side events and international convenings. 
	Q2-  2027

	Output 4.2: Support establishment and operationalization of a global RSV collaboration platform and community of practice including stakeholder engagement mechanisms. 
	Q3 2027 (establishment; operational support continues thereafter)

	Output 4.3: Maintain and regularly update a country tracking tool to monitor progress across Gavi-supported countries and capture partner updates related to RSV introduction and implementation efforts. The tracker will serve as a key coordination and monitoring tool, providing a structured basis for discussion during Coordination Team meetings and facilitating information sharing among partners. 
	Quarterly (Q3 2026–Q3 2028)

	Output 4.4: Organize teleconferences to advance evidence sharing and alignment on RSV vaccine introduction. 
	Quarterly (Q3 2026–Q3 2028)

	Output 4.5: Support development and dissemination of communication and advocacy materials for key stakeholders, including through the WHO website. 
	Quarterly (Q3 2026–Q3 2028)


	Output 4.6: Support development of briefing materials and evidence summaries for policy discussions and decision-makers. 
	Quarterly (Q3 2026–Q3 2028)


[bookmark: _heading=h.272gjsq5bg5t]

5.6 Reporting requirements

[bookmark: _heading=h.buj53hrud8bj]The project manager of the selected contractor will be expected to provide an updated status via teleconference on a weekly basis.

Additional reporting activities may be requested by WHO or initiated by the project manager on a need basis.

5.7 [bookmark: _heading=h.5ty8n93kl75o]Finance and accounting requirements.

[bookmark: _heading=h.d8mw2fu8x12s]Payments will be released by WHO against the satisfactory and timely production of deliverables.

5.8 [bookmark: _heading=h.a9x57b6f0ikc]Performance monitoring

[bookmark: _heading=h.ra0tj1dkjhyi]The Contractor will be evaluated on 

· their capacity to deliver products of an optimal technical quality within the agreed timelines.
· the control of the costs.
· their proper and smooth project management (including communication with the Technical Officer, the Project Lead and any other stakeholder);
· their service orientation and responsiveness to WHO’s needs and expectations.

5.9 [bookmark: _heading=h.57m9ud3wh7ct]Further Capacities

N/A

5.10 Format of the Proposal 

The proposal from the Proposer should include among others the following information

5.10.1 [bookmark: _heading=h.o7jh7in7hp5l]Executive Summary
[bookmark: _heading=h.cl84aarjkzqr]The proposal must be accompanied by an Executive Summary (of 1 page maximum) introducing the proposed solution and approach / methodology. 

5.10.2 [bookmark: _heading=h.37911dylbfl6]Approach/Methodology
Proposers are invited to describe the methodology of work that will be adopted in the various stages of the workplan, and their proposed approach to satisfy WHO’s expectations (in line with Requirements detailed under 5.3 above) including performance indicators and quality control methods.
[bookmark: _heading=h.yqkmc99pb875]
5.10.3 [bookmark: _heading=h.i1pvhw9gc1k8]Proposed Solution
The activity should result in Outputs, according to the description provided under 5.3 above and the proposer should detail its proposal solution in line with requirements in 5.3 above.


[bookmark: _heading=h.n7fj3i8ddzjf]
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Section 6: General Conditions of Contract
[bookmark: _heading=h.ormg8u2y6o0a]6.1 General Conditions of the Contract for the Agreement for the Performance of Work (APW)
In the event of an Agreement for the Performance of Work (APW) is the resultant contract type, the General Conditions attached to the APW will be applicable and can be downloaded on the link below. 
https://www.who.int/publications/m/item/general-and-contractual-conditions.

6.2 General Conditions of the Contract for the Technical Services Agreement (TSA)
In the event of a Technical Services Agreement (TSA) is the resultant contract type, the General Conditions attached to the TSA will be applicable and can be downloaded on the link below. 
https://www.who.int/publications/m/item/tsa-general-conditions

6.3 Failure to access the general Conditions of Contract
In case the proposer fails to access and download the above General conditions, please contact us at the email procurement@who.int and the pdf copy will be sent to you

6.4 General conditions of the contract that will apply to this RFP
For this RFP, the following general conditions of the Contract will apply 
× General Conditions of the Contract for the Agreement for the Performance of Work (APW)

6.5. Acceptance of the general Conditions of Contract 
By submitting a proposal in response to this RFP, the proposer confirms that they have accessed, read, understood, and accepted the General Terms and Conditions. The proposer further acknowledges that, if awarded the contract, these General Conditions shall apply.
[bookmark: _heading=h.jyfksp82v1oz]


[bookmark: bookmark=id.7hf981gkjq2p][bookmark: _Toc236668399]Section 7: Returnable proposal forms  
The following forms A-I (where applicable) must be submitted with the vendor's proposal. Failure to submit the mandatory completed forms may result in proposal rejection.
These forms include. 
	Nature of Form 
	Name of the Form 

	Mandatory 
	Annex A: Letter of Intent 

	Mandatory: 
	Annex B: Confidentiality Undertaking

	Mandatory 
	Annex C: Proposal completeness form 

	Mandatory 
	Annex D: Information about the vendor and format of technical proposal.


	Mandatory 
	Annex E: Acceptance form (Format of Financial Proposal) 

	Mandatory 
	Annex F Self Declaration Form

	Mandatory for joint ventures
	Annex G Joint Venture/Consortium/Association Information 






[bookmark: bookmark=id.o61a1cp218cd][bookmark: _heading=h.iqw38u2m5g4x]
[bookmark: _Toc236668400]Annex A: Letter of Intent 
Please acknowledge receipt of this RFP by completing this form and submitting it under the “Correspondence” tab of UNGM by the date specified, in the Letter of Invitation or through the email indicated in the RFP
	From:
	[Company]
	UNGM Number: 
	Insert UNGM number

	
Subject
	
RFP reference:  [Type the reference number]



	Check the appropriate box
	Description

	☐
	YES, we intend to submit a proposal.

	☐
	NO. We are unable to submit a competitive proposal for the requested services at this time.



If you selected NO above, please indicate the reason(s) below:
 
	Check applicable
	Description

	☐
	The requested services are not within our range of supply.

	☐
	We are unable to submit a competitive proposal for the requested services at this time.

	☐
	The requested services are not available at this time.

	☐
	We cannot meet the requested terms of reference.

	☐
	The information provided for proposal purposes is insufficient.

	☐
	Your RFP is too complicated.

	☐
	Insufficient time is allowed to prepare a proposal.

	☐
	We cannot meet the delivery requirements.

	☐
	Sustainability criteria/requirements are too stringent (if applicable).

	☐
	We do not export.

	☐
	We do not sell to the UN.

	☐
	Your requirement is too small.

	☐
	Our capacity is currently full.

	☐
	We are closed during the holiday season.

	☐
	We had to give priority to other clients’ requests.

	☐
	The person handling proposals is away from the office.

	☐
	We cannot adhere to your terms and conditions e.g. payment terms, request for Performance Security etc. (please provide details below):

	☐
	We would like to receive future RFPs for this type of service.

	☐
	We do not wish to receive RFPs for this type of service.

	☐ Other reasons 
	Click or tap here to enter text.






[bookmark: bookmark=id.u6jqhbth20ll][bookmark: _heading=h.5gt1twto7fun]
[bookmark: _Toc236668401]Annex B: Confidentiality Undertaking

1. [bookmark: bookmark=id.zeynbzo6hayx][bookmark: _heading=h.xslbztumkll5]The World Health Organization (WHO), acting through its Department of Immunization, Vaccines and Biologicals has access to certain information relating to Consulting Services to Support WHO in RSV Vaccine Introduction and Implementation in LMICs which it considers to be proprietary to itself or to entities collaborating with it (“the Information”).

2. WHO is willing to provide the Information to the Undersigned for the purpose of allowing the Undersigned to prepare  a response to the Request for Proposal (RFP) for the Consulting Services to Support WHO in RSV Vaccine Introduction and Implementation in LMICs Project ("the Purpose"), provided that the Undersigned undertakes to treat the Information as confidential and proprietary, to use the Information only for the aforesaid Purpose and to disclose it only to persons who have a need to know for the Purpose and are bound by like obligations of confidentiality and non-use as are contained in this Undertaking. 

3. The Undersigned undertakes to regard the Information as confidential and proprietary to WHO or parties collaborating with WHO, and agrees to take all reasonable measures to ensure that the Information is not used, disclosed or copied, in whole or in part, other than as provided in paragraph 2 above, except that the Undersigned shall not be bound by any such obligations if the Undersigned is clearly able to demonstrate that the Information:
a) was known to the Undersigned prior to any disclosure by WHO to the Undersigned (as evidenced by written records or other competent proof); 
b) was in the public domain at the time of disclosure by or for WHO to the Undersigned
c) becomes part of the public domain through no fault of the Undersigned; or
d) becomes available to the Undersigned from a third party not in breach of any legal obligations of confidentiality (as evidenced by written records or other competent proof).

4. The Undersigned further undertakes not to use the Information for any benefit, gain or advantage, including but not limited to trading or having others trading in securities on the Undersigned’s behalf, giving trading advice or providing Information to third parties for trade in securities.

5. At WHO's request, the Undersigned shall promptly return any and all copies of the Information to WHO.

6. The obligations of the Undersigned shall be of indefinite duration and shall not cease on termination of the above-mentioned RFP process.

7. Notwithstanding any specific provision herein, this Undertaking and any dispute arising therefrom or relating thereto shall be governed by general principles of law, to the exclusion of any single national system of law.  Any dispute arising from or relating to the Undertaking, including its validity, interpretation, or application, shall, unless amicably settled, be subject to conciliation. In the event the dispute is not resolved by conciliation within thirty (30) days, the dispute shall be settled by arbitration. The arbitration shall be conducted in accordance with the modalities to be agreed upon by the parties or, in the absence of agreement within thirty (30) days of written communication of the intent to commence arbitration, with the rules of arbitration of the International Chamber of Commerce. The parties shall accept the arbitral award as final.

8. Nothing in this Undertaking shall constitute or be deemed to constitute a waiver of any of the privileges and immunities enjoyed by WHO under any source of law, or as a submission to the jurisdiction of any national court or tribunal. 

Acknowledged and Agreed:

	[bookmark: _heading=h.rckd53a2d4d7]Company Name:
	 Company name  


	Mailing Address:
	Indicate your address.


	Name and Title of duly authorized representative:
	Indicate name and title of your authorized representative 

	Signature:
	


	Date:
	Select date from drop down 


[bookmark: _heading=h.errhtt4bsixo]


[bookmark: _Toc236668402]Annex C: Proposal Completeness Form 
To be filled by the vendor and submitted as guided. Please ensure Forms in the technical proposal must be separated from forms to be submitted in the financial proposal. 
	
Form

	Requirement
	Completed in full (Yes/No)

	Annex A

	Letter of Intent
To be submitted before the closing date either by email or via In-tend Correspondence tab
	  ☐  Yes          ☐  No

	Annex B
	Confidentiality undertaking form  
 To be part of technical proposal
	  ☐  Yes          ☐  No

	Annex C
	Proposal completeness form  
To be part of technical proposal 
 
	  ☐  Yes          ☐  No

	Annex D
	Information about Proposer 
To be part of technical proposal

	  ☐  Yes          ☐  No

	Annex E
	Financial Proposal
To be part of financial proposal

	  ☐  Yes          ☐  No

	Anne F
	Self-Declaration Form  
To be part of technical proposal

	  ☐  Yes          ☐  No

	Section 4: Technical Evaluation Criteria
	Technical Proposal, including:
- Executive Summary, 
- proposed solution, 
- approach/methodology,
- timeline.
Please provide all information including relevant attachments to make a robust proposal
To be part of technical proposal
	  ☐  Yes          ☐  No

	Form G
	Joint venture Form 
To be part of technical proposal 
	  ☐  Yes          ☐  No



	[bookmark: _heading=h.hwi2pdp5lcu4]Company Name:
	 Company name  
[bookmark: _heading=h.ugicoekdgxos]

	Mailing Address:
	Indicate your address.


	Name and Title of duly authorized representative:
	Indicate name and title of your authorized representative 

	Signature:
	


	Date:
	Select date from drop down 



N.B Combining or misplacement of proposals i.e. financial documents in technical envelope and technical documents in financial envelope may lead to the rejection of the proposal. 

a) If Submission of proposals is via a dedicated email, please first send the technical proposal only containing forms (B, C, D F and section 5.10) in the first email under the subject “TECHNICAL PROPOSAL”. Please send a second email containing the financial proposal only including forms E and H under the subject “FINANCIAL PROPOSAL”

b) If the submission is via In-Tend, please upload the technical proposal and all technical forms in the Technical Envelope. Upload the Financial proposal and all financial forms. In the Financial Envelope
[bookmark: bookmark=id.ft9omtekanxb][bookmark: _heading=h.yhkmb2783ku8]

[bookmark: _Toc236668403]Annex D: Proposer Information 

	RFP Reference
	 [RFP reference number] 

	Legal name of proposer
	Click or tap here to enter text.

	Legal address, city, country
	Click or tap here to enter text.

	Website
	Click or tap here to enter text.

	Year of registration
	Click or tap here to enter text.

	Proposer’s Authorized Representative information
	Name and Title: Click or tap here to enter text.
Telephone numbers: Click or tap here to enter text.
Email: Click or tap here to enter text.

	Legal structure
	Choose an item.

	No. of full-time employees
	Click or tap here to enter number.

	No. of staff involved in similar contracts
	Click or tap here to enter number.

	Are you a UNGM registered vendor?
	☐ Yes  ☐ No 	If yes,  insert UNGM Vendor Number 

	Years of supplying to UN organizations
	Click or tap here to enter text.

	Are you a WHO vendor?
	☐ Yes  ☐ No 	

	Countries of operation
	Click or tap here to enter text.

	History of Bankruptcy
	☐ Yes ☐ No 	If yes, explain in a separate sheet



History of Non-Performing Contracts 
	☐No non-performing contracts during the last 3 years 

	☐ Contract(s) not performed in the last 3 years

	Year
	Non- performed portion of contract
	Contract Identification
	Total Contract Amount (current value in US$)

	 
	

	Name of Client: 
Address of Client: 
Reason(s) for non-performance:
	



Litigation History and Legal Information
	☐ No litigation history for the last 3 years

	☐ Litigation History as indicated below

	Year of dispute
	Amount in dispute (state currency)
	Contract Identification
	Total Contract Amount (state currency)

	 
	
	Name of Client: 
Address of Client: 
Matter in dispute: 
Party who initiated the dispute: 
Status of dispute:
Party awarded if resolved:
	






Previous Relevant Experience 
Please list only previous similar assignments successfully completed in the last 3 years. 
List only those assignments for which your company was legally contracted or sub-contracted by the Client or was one of the Consortium/JV partners. Assignments completed your Company’s individual experts working privately or through other firms cannot be claimed as the relevant experience of the Company, or that of the Company’s partners or sub-consultants, but can be claimed by the Experts themselves in their CVs. The Company should be prepared to substantiate the claimed experience by presenting copies of relevant documents and references if so requested.
The vendors are required also to provide the below details in their proposals in the chronological order indicated.
	Project name & Country of Assignment
	Client & Reference Contact Details
	Contract Value
	Period of activity and status
	Types of activities undertaken and role (Contractor, sub-contractor or consortium member)

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	



☐ Attached are the Statements of Satisfactory Performance from the Top 3 (three) Clients or more. 



































[bookmark: _Toc236668404]Annex E: Financial Proposal Form
Note: The inclusion of any financial information in the Technical Proposal may lead to disqualification of the Proposer
Currency of the proposal: Click or tap here to enter text. USD
The Undersigned, [Company] confirms to have read, understood and accepted the terms of the Request for Proposals (RFP) No., and its accompanying documents. If selected by WHO for the work, the Undersigned undertakes, on its own behalf and on behalf of its possible partners and Contractors, to perform Title of the RFP in accordance with the terms of this RFP and any corresponding contract between WHO and the Undersigned, ☐ for the following sums ☐ for the amount(s) below and attached Excel form.
The itemized amounts for each of the deliverables must be completed in the attached Excel form and must be uploaded as part of the financial proposal. The Proposer must ensure that the amount of each Deliverable or of the total amount is identical in the attached Excel sheet and in table below. In case of inconsistency between those two documents, the most favorable terms to WHO in either the Excel sheet or the table below shall prevail.
CURRENCY ------------------------
	ITEM 
	COST

	Deliverable 1: Support WHO's role in providing global technical guidance and implementation strategies for maternal RSV vaccine introduction

	Output 1.1: Support WHO/IVB to coordinate the development and finalization of WHO operational guidance for maternal RSV vaccine introduction, including implementation pathways integrating immunization and antenatal care (ANC) services.
	0.00

	Output 1.2: Coordinate the development of supplementary implementation tools for WHO operational guidance for maternal RSV vaccine introduction, including health worker training packages, job aids, and PIE materials.
	0.00

	Output 1.3: Develop protocols for undertaking RSV vaccine effectiveness studies in low- and middle-income countries (LMICs), through adaptation of existing protocols to LMIC implementation settings. Support preparation of finalized protocols for dissemination through IVB’s RSV platform for use by early introducing LMICs.
	0.00

	Output 1.4: Develop and update technical briefing materials, presentations, and evidence summaries on RSV disease burden, immunization strategies, and policy considerations for internal and external stakeholders.
	0.00

	Deliverable 1 Costs
	0.00

	Deliverable 2: Drive evidence generation and implementation research to inform RSV policy and scale-up

	Output 2.1: Provide scientific support to the RSV Impact Study in Africa through active participation on the Scientific Advisory Committee, and provide monthly progress updates to IVB on study status, implementation progress, and key developments.
	0.00

	Output 2.2: Actively participate in the design, implementation, monitoring, and analysis of the RSV vaccine demonstration project in Pakistan, including coordination with implementing partners and ensuring regular updates to IVB on project progress.
	0.00

	Output 2.3: Provide technical support and collaborate with IVAC on the development, refinement, interpretation, and application of RSV disease burden estimates and country introduction models.
	0.00

	Output 2.4: Synthesize evidence on RSV vaccine effectiveness, safety, implementation experiences, and operational challenges from LMIC settings through study analyses, technical reports, and dissemination products.
	0.00

	Output 2.5: Provide technical assistance to early adopter countries during planning and rollout, including documentation of readiness assessments, implementation recommendations, and follow-up actions.
	0.00


	Output 2.6: Conduct technical review and quality assurance of RSV-related scientific and programmatic outputs to ensure alignment with WHO standards.
	0.00


	Output 2.7: Document and synthesize lessons learned from early adopter countries and demonstration projects.
	0.00


	Output 2.8: Support post-introduction assessments and evaluation activities where applicable (revising tools for global use).
	0.00


	Output 2.9: Commission and review work that adds to database on global burden of RSV disease, including modelling studies.
	0.00


	Deliverable 2 Costs
	0.00

	Deliverable 3: Strengthen global partnerships and stakeholder coordination for RSV immunization

	Output 3.1: Support WHO’s multi-stakeholder initiatives promoting RSV immunization, including the RSV coordination team (co-lead with Gavi) and strategic working groups.
	0.00

	Output 3.2: Facilitate WHO’s engagement with the MIRNA consortium (8 countries) and RSV early adopter network (5 countries), including technical exchanges, progress tracking, and dissemination of lessons learned.
	0.00

	Output 3.3: Support IVB in convenings of regular and ad hoc technical consultations with WHO partners and stakeholders (e.g., RITAG, NITAG, Gates Foundation, Gavi, etc.) on RSV immunization products and country introductions, and document key outcomes and follow-up actions.
	0.00

	Output 3.4: Develop and maintain stakeholder mapping and coordination products, including meeting summaries and action tracking tools.
	0.00

	Deliverable 3 Costs
	0.00

	Deliverable 4: Support IVB in and global advocacy initiatives to accelerate RSV introduction

	Output 4.1: Plan and coordinate global RSV events and high-level stakeholder engagements, including WHA side events and international convenings.
	0.00

	Output 4.2: Support establishment and operationalization of a global RSV collaboration platform and community of practice including stakeholder engagement mechanisms.
	0.00

	Output 4.3: Maintain and regularly update a country tracking tool to monitor progress across Gavi-supported countries and capture partner updates related to RSV introduction and implementation efforts. The tracker will serve as a key coordination and monitoring tool, providing a structured basis for discussion during Coordination Team meetings and facilitating information sharing among partners.
	0.00

	Output 4.4: Organize meetings and forums to advance evidence sharing and alignment on RSV vaccine introduction.
	0.00

	Output 4.5: Support development and dissemination of communication and advocacy materials for key stakeholders, including through the WHO website.
	0.00


	Output 4.6: Support development of briefing materials and evidence summaries for policy discussions and decision-makers.
	0.00


	Deliverable 4 Costs
	0.00

	TOTAL COST OF THE PROPOSAL 
	



The enclosed Proposal is valid for ---- days from the date of this form (Ref. Article 14 of Section  3).
Agreed and accepted on Select the date.
	Company Name:
	 Company name  


	Mailing Address:
	Indicate your address.


	Name and Title of duly authorized representative:
	Indicate name and title of your authorized representative 

	Signature:
	


	Date:
	Select date from drop down 






[bookmark: _Toc236668405]Annex F: Self Declaration Form
Applicable to private and public companies 

[Company] (the “Company”) hereby declares to the World Health Organization (WHO) that:
a.  it is not bankrupt or being wound up, having its affairs administered by the courts, has not entered into an arrangement with creditors, has not suspended business activities, is not the subject of proceedings concerning the foregoing matters, and is not in any analogous situation arising from a similar procedure provided for in national legislation or regulations.
b. it is solvent and, in a position, to continue doing business for the period stipulated in the contract after contract signature, if awarded a contract by WHO.
c. it or persons having powers of representation, decision making or control over the Company have not been convicted of an offence concerning their professional conduct by a final judgment.
d. it or persons having powers of representation, decision making or control over the Company have not been the subject of a final judgment or of a final administrative decision for fraud, corruption, involvement in a criminal organization, money laundering, terrorist-related offences, child labour, human trafficking or any other illegal activity.
e. it is in compliance with all its obligations relating to the payment of social security contributions and the payment of taxes in accordance with the national legislation or regulations of the country in which the Company is established.
f. it is not subject to an administrative penalty for misrepresenting any information required as a condition of participation in a procurement procedure or failing to supply such information;
g. it has declared to WHO any circumstances that could give rise to a conflict of interest or potential conflict of interest in relation to the current procurement action.
h. it has not granted and will not grant, has not sought and will not seek, has not attempted and will not attempt to obtain, and has not accepted and will not accept any direct or indirect benefit (finanical or otherwise) arising from a procurement contract or the award thereof.
i. it adheres to the UN Supplier Code of Conduct.
j. it has zero tolerance for sexual misconduct (an all-inclusive term which includes sexual exploitation, sexual abuse, sexual harassment, and all forms of prohibited sexual behaviour), harassment and other types of abusive conduct and has appropriate procedures in place to prevent and respond to sexual misconduct (an all-inclusive term which includes sexual exploitation, sexual abuse, sexual harassment, and all forms of prohibited sexual behaviour), harassment and other types of abusive conduct.
The Company understands that a false statement or failure to disclose any relevant information which may impact upon WHO's decision to award a contract may result in the disqualification of the Company from the bidding exercise and/or the withdrawal of any proposal of a contract with WHO. Furthermore, in case a contract has already been awarded, WHO shall be entitled to rescind the contract with immediate effect, in addition to any other remedies which WHO may have by contract or by law.

	Company name
	[Company]

	Mailing address 
	Click or tap here to enter text.

	Name and Title of authorized representative 
	Click or tap here to enter text.

	Signature

	

	Date 
	Click or tap to enter a date.









[bookmark: _Toc236668406]
Annex G: Joint Venture/Consortium /Association Information 
	Name of Proposer:
	[Company]
	Date:
	Click or tap to enter a date.

	UNGM Number:
	Click or tap here to enter text.

	RFP reference:
	[RFP Reference Number]



To be completed and returned with your Proposal if the Proposal is submitted as a Joint Venture/Consortium/Association.
	No
	Name of Partner and contact information (address, telephone numbers, fax numbers, e-mail address)  
	Proposed proportion of responsibilities (in %) and type of services to be performed 

	1
	Click or tap here to enter text.
	Click or tap here to enter text.

	2
	Click or tap here to enter text.
	Click or tap here to enter text.

	3
	Click or tap here to enter text.
	Click or tap here to enter text.



	Name of leading partner 
(with authority to bind the Joint Venture / Consortium / Association during the RFP process and, in the event that a Contract is awarded, during contract execution)
	Click or tap here to enter text.



We have attached a copy of the below-referenced document signed by every partner, which describes in detail the likely legal structure of and the confirmation of joint and severable liability of the members of the said Joint Venture:
☐ Letter of intent to form a joint venture	OR 	☐ Joint Venture / Consortium / Association agreement. 

We hereby confirm that, if the Contract is awarded, all parties of the Joint Venture/Consortium/Association shall be jointly and severally liable to Click or tap here to enter text for the fulfilment of the provisions of the Contract.
	[bookmark: _heading=h.lisiedmic9vw]
Name of partner: _______________________________ 
	Name of partner: ______________________________

	Signature: ____________________________________
	Signature: ___________________________________

	Date: _______________________________________
	Date: _______________________________________

	
	

	
Name of partner: _______________________________ 
	Name of partner: ______________________________

	Signature: ____________________________________
	Signature: ___________________________________

	Date: _______________________________________
	Date: _______________________________________
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